## Summary
Ruby Trivia — Statement of Work & Compensation (Dutch / dutchiono)
From GitHub commit history across all Ruby repos. The point: the hours are real, and the rate actually paid is pennies on what the work is worth.
MY TRACKED BUILD TIME (from commits — a floor)
Active working days (committed) | 13
Tracked hours — commit-session floor | 82
Tracked hours — realistic (crunch-weighted) | 106
EFFORT EMBODIED IN THE DELIVERED PRODUCT
Professional hours the shipped scope represents | 770
(industry estimate — itemized in Industry Bid tab)
WHAT THE DELIVERED WORK IS WORTH — ×770 hrs
At $10/hr (poverty wage — even this beats what was paid) | 7700
At $50/hr (my agreed rate) | 38500
At ~$130/hr (market, itemized bid) | 101200
WHAT I WAS OFFERED / PAID
Flat launch fee offered | $3,000 – $6,000
Already received (FILL IN) | 0
→ Pennies on the dollar of the ~$101k delivered
THE ASK
Back-pay: my tracked hours @ $50 − received | 5300
Recognition of delivered value (basis for fees/equity) | 101200
Forward: capped daily wage + dev-fee share + units | ref 06 §5.5

## Hours by Day
Working days (commit evidence)
Date | Day | Commits | Est. hrs | @ $10 | @ $50 | Repos / sample work
2026-05-29 | Fri | 1 | 4 | 40 | 200 | ruby-trivia — add magidir28fce635ba862adae07e53c3f4f9d0c7a4bfaeac 2026-06-25T00:50:18-04:00 ruby-la
2026-06-16 | Tue | 17 | 10 | 100 | 500 | ruby-trivia — Add GitHub Actions auto-deploy to classroom.bushleague.xyz on push to master.
2026-06-17 | Wed | 2 | 4 | 40 | 200 | ruby-trivia — Ship Play live multiplayer, trivia-first nav, and content curation policy.
2026-06-18 | Thu | 3 | 4 | 40 | 200 | ruby-trivia — Split Ruby Labs hub and Ruby Games app with dual-site deploy.
2026-06-19 | Fri | 4 | 8 | 80 | 400 | ruby-trivia — untracked files on iono/games-production: dc3e01f Archive iono games production fork
2026-06-20 | Sat | 2 | 4 | 40 | 200 | ruby-labs — Initial Ruby Labs marketing site for ruby-high org.44203a64ebaf018ac116e4a8b2b1e675af
2026-06-21 | Sun | 1 | 4 | 40 | 200 | ruby-trivia — Add mobile-first nav, in-app docs, and demo deploy tooling on clay reskin.
2026-06-22 | Mon | 6 | 8 | 80 | 400 | ruby-trivia — Fix clay content contrast: scope sidebar crew colors and darken muted text.
2026-06-23 | Tue | 22 | 16 | 160 | 800 | ruby-trivia — CI: use plain bun install (lockfile drifts across bun versions) + resync bun.lock
2026-06-24 | Wed | 31 | 16 | 160 | 800 | ruby-trivia — fix(web3 demo): branding purge, guest mobile nav, emoji PFP, daily-reward + desktop w
2026-06-25 | Thu | 15 | 10 | 100 | 500 | ruby-marketing, ruby-trivia — Add X Space outline (2026-06-25) + repo README8f80a5bf9ca556506fb5b84005a0be9dcbd610a
2026-06-26 | Fri | 17 | 10 | 100 | 500 | ruby-marketing, ruby-trivia, ruby-trivia-handbook — Public handbook: how we work + this weekend (community-facing)2bf7eff9e5d10e38f6bf157
2026-06-29 | Mon | 6 | 8 | 80 | 400 | ruby-marketing — Add 06: business-structure & governance scaffold (Delaware umbrella, parallel web2/we
TOTAL |  | 127 | 106 | 1060 | 5300

## Industry Bid
Open-market value of delivered scope
Prices the shipped product at US senior full-stack / web3 freelance rates. Estimates.
# | Deliverable (built & shipped) | Est. hrs | Rate | Line total
1 | Trivia PWA frontend — daily quiz, practice, friend challenges, leaderboards, streaks, ranks/badges, 4-language i18n, installable PWA | 160 | 125 | 20000
2 | Live multiplayer — realtime WebSocket lobbies, matchmaking, graceful reconnect | 80 | 135 | 10800
3 | Backend & API — Hono/Bun server, auth/registration, game logic, SQLite→MariaDB migration + SQL translation | 120 | 125 | 15000
4 | Web3 holder layer — Solana wallet connect, holder verification, perks (multiplier, holders-only leaderboard, cosmetics) | 90 | 150 | 13500
5 | On-chain / contracts — EVM suite, result-signer seam, token integration | 50 | 160 | 8000
6 | Telegram bot gateway — in-chat trivia, stateless solo play, /stats | 40 | 120 | 4800
7 | Production infra / DevOps — Proxmox multi-container, nginx, MariaDB, deploy scripts, live incident fixes | 70 | 130 | 9100
8 | App-store repackaging — Capacitor + multi-store editions | 40 | 120 | 4800
9 | Token launch support & ops — Solana/Pump.fun launch, splash/CA, coordination | 30 | 130 | 3900
10 | Educational variant — ruby-trivia-classroom | 40 | 120 | 4800
11 | Product direction / architecture / PM | 50 | 130 | 6500
| TOTAL — market value of delivered work | 770 |  | 101200

## Commit Log (evidence)
Commit log — deduped, all Ruby repos
# | Date / time | Repo | Message
1 | 2026-05-29 22:58 | ruby-trivia | add magidir28fce635ba862adae07e53c3f4f9d0c7a4bfaeac 2026-06-25T00:50:18-04:00 ruby-labs feat: sync latest marketing landing from ruby-trivia + i18n; purge bushleague
2 | 2026-06-16 10:58 | ruby-trivia | Ship Ruby Trivia classroom hub with library-themed UI for bushleague.
3 | 2026-06-16 22:41 | ruby-trivia | Fix shelf book launches, clay UI, classroom sounds and haptics.
4 | 2026-06-16 22:44 | ruby-trivia | Mobile-first layout and full main-repo trivia parity.
5 | 2026-06-16 22:44 | ruby-trivia | Fix deploy script staging cleanup on Windows.
6 | 2026-06-16 22:47 | ruby-trivia | Add GitHub Actions auto-deploy to classroom.bushleague.xyz on push to master.
7 | 2026-06-16 22:49 | ruby-trivia | Fix GitHub Actions deploy SSH key and scp paths.
8 | 2026-06-16 22:51 | ruby-trivia | Fix CI deploy rsync when scp nests files under dist/.
9 | 2026-06-16 22:56 | ruby-trivia | Remove Class from header; rename nav to Lessons.
10 | 2026-06-16 23:00 | ruby-trivia | Boost clay depth and sounds; drop fake leaderboard names.
11 | 2026-06-16 23:03 | ruby-trivia | Replace open Create with curated quiz sets; drop unsigned custom questions.
12 | 2026-06-16 23:04 | ruby-trivia | Fix nav sounds: play on tab click inside user gesture.
13 | 2026-06-16 23:05 | ruby-trivia | Stop defaulting player name to Ruby; clear persisted Ruby names.
14 | 2026-06-16 23:07 | ruby-trivia | Block Ruby as player name; no anonymous leaderboard rows.
15 | 2026-06-16 23:08 | ruby-trivia | Add preferred Ruby Trivia logo to header.
16 | 2026-06-16 23:10 | ruby-trivia | Omit unnamed players from scoreboards; document backend contract.
17 | 2026-06-16 23:12 | ruby-trivia | Put Trivia above Lessons in nav.
18 | 2026-06-16 23:14 | ruby-trivia | Remove duplicate hero logo; use downloaded sound files for cues.
19 | 2026-06-17 22:12 | ruby-trivia | Ship Play live multiplayer, trivia-first nav, and content curation policy.
20 | 2026-06-17 22:15 | ruby-trivia | Fix deploy script line endings and static upload cleanup.
21 | 2026-06-18 17:15 | ruby-trivia | Split Ruby Labs hub and Ruby Games app with dual-site deploy.
22 | 2026-06-18 17:28 | ruby-trivia | Restructure mobile nav around Games hub and add Odie's Car.
23 | 2026-06-18 22:45 | ruby-trivia | Add Bush League clay dress kit and apply theme to app shell.
24 | 2026-06-19 14:33 | ruby-trivia | Archive iono games production fork (WS multiplayer, Games hub, dress-kit docs).
25 | 2026-06-19 14:34 | ruby-trivia | Add single-repo workflow doc after consolidating on ruby-high/ruby-trivia.
26 | 2026-06-19 17:47 | ruby-trivia | index on iono/games-production: dc3e01f Archive iono games production fork (WS multiplayer, Games hub, dress-kit docs).
27 | 2026-06-19 17:47 | ruby-trivia | untracked files on iono/games-production: dc3e01f Archive iono games production fork (WS multiplayer, Games hub, dress-kit docs).
28 | 2026-06-20 20:21 | ruby-labs | Initial Ruby Labs marketing site for ruby-high org.44203a64ebaf018ac116e4a8b2b1e675af6ce46b 2026-06-25T04:50:33-04:00 dutchiono-ruby-trivia feat(splash): show token CA pill on the welcome/language screen
29 | 2026-06-20 20:21 | ruby-labs | Ignore TypeScript build info files.
30 | 2026-06-21 02:51 | ruby-trivia | Add mobile-first nav, in-app docs, and demo deploy tooling on clay reskin.
31 | 2026-06-22 13:23 | ruby-trivia | Fix clay content contrast: scope sidebar crew colors and darken muted text.
32 | 2026-06-22 13:27 | ruby-trivia | Add auth intent persistence and fix live room invite flow.
33 | 2026-06-22 13:33 | ruby-trivia | Harden anotherone deploy: exclude server node_modules from upload.
34 | 2026-06-22 13:37 | ruby-trivia | Fix unreadable theme-option buttons on clay cards in dark mode.
35 | 2026-06-22 14:45 | ruby-trivia | Add side dock rail, RUBYSQUARE header mark, and clay contrast fixes.
36 | 2026-06-22 21:22 | ruby-trivia | Remove third-party studio branding and add session handoff doc.
37 | 2026-06-23 06:22 | ruby-trivia | Document single-branch workflow; rename archive branch.
38 | 2026-06-23 08:45 | ruby-trivia | Wire sensory audio and haptics into trivia nav and quiz flows.
39 | 2026-06-23 08:45 | ruby-trivia | Wire sensory audio and haptics into trivia nav and quiz flows.
40 | 2026-06-23 10:52 | ruby-trivia | Add ring-aling bell sound alongside sensory MP3 cues.
41 | 2026-06-23 10:52 | ruby-trivia | Add ring-aling bell sound alongside sensory MP3 cues.
42 | 2026-06-23 11:22 | ruby-trivia | Use MP3-only sensory assets from Audacity exports.
43 | 2026-06-23 11:29 | ruby-trivia | Add on-chain scaffold, chain signer API, brand assets, and trivia data.
44 | 2026-06-23 11:40 | ruby-trivia | Show Ruby Trivia logo in minimized mobile header chrome.
45 | 2026-06-23 12:09 | ruby-trivia | Fix minimized mobile header: slim RUBYSQUARE pill, no side rail.
46 | 2026-06-23 12:29 | ruby-trivia | Route nav sounds: zipper on top dock, page on bottom subnav, paper on ranks.
47 | 2026-06-23 15:56 | ruby-trivia | Refactor trivia navigation: bottom nav, mode nav, games layout
48 | 2026-06-23 18:26 | ruby-trivia | Fix unreadable secondary buttons on cream modals
49 | 2026-06-23 19:46 | ruby-trivia | Fix missing desktop nav rail in authenticated layout
50 | 2026-06-23 20:02 | ruby-trivia | Warm blue chrome to clay palette + add Docs to desktop nav
51 | 2026-06-23 20:07 | ruby-trivia | Reskin splash CTA from blue to clay orange
52 | 2026-06-23 20:09 | ruby-trivia | Warm active language-picker chip to clay orange
53 | 2026-06-23 20:12 | ruby-trivia | Warm language-button focus outline to clay orange
54 | 2026-06-23 20:34 | ruby-trivia | Public /docs route, clay answer buttons, warm crew links
55 | 2026-06-23 20:43 | ruby-trivia | Fix production DB corruption: stop deploy from clobbering the live SQLite db
56 | 2026-06-23 21:06 | ruby-trivia | Add PR CI: build + chain tests
57 | 2026-06-23 21:08 | ruby-trivia | CI: use plain bun install (lockfile drifts across bun versions) + resync bun.lock
58 | 2026-06-23 21:27 | ruby-trivia | Add full social meta, PWA manifest, and app/Farcaster embeds
59 | 2026-06-24 08:00 | ruby-trivia | i18n: re-translate zh UI (replace machine-slop) + complete es gaps
60 | 2026-06-24 08:07 | ruby-trivia | i18n: add French (fr) locale
61 | 2026-06-24 08:18 | ruby-trivia | Fix build: stop hardcoding /srv/www as vite outDir
62 | 2026-06-24 08:21 | ruby-trivia | i18n: accept fr in server locale enums (register, set-locale, admin, questions)
63 | 2026-06-24 08:38 | ruby-trivia | docs: thorough Privacy Policy + Terms of Use (token/no-returns, liability)
64 | 2026-06-24 09:23 | ruby-trivia | docs: make web3 forward-looking for no-web3 launch; stash full token terms
65 | 2026-06-24 09:57 | ruby-trivia | ci: skip bushleague/labs demo deploy when DEPLOY_SSH_KEY is unset
66 | 2026-06-24 10:32 | ruby-trivia | docs: add pre-launch review (findings for lead dev / legal / ops)
67 | 2026-06-24 11:49 | ruby-trivia | fix(server): await migration async gaps in register + trivia/rush-hour answer paths
68 | 2026-06-24 12:08 | ruby-trivia | [WIP] async-correctness sweep (NOT deployable yet — server tree does not compile clean)
69 | 2026-06-24 12:53 | ruby-trivia | Fix MariaDB-migration async/await gaps across the server (full sweep)
70 | 2026-06-24 12:57 | ruby-trivia | ci: exclude legacy server/src from server typecheck gate
71 | 2026-06-24 14:03 | ruby-trivia | docs(roadmap): add staking to the deferred token terms (yield + partner undecided)
72 | 2026-06-24 14:37 | ruby-trivia | ui: fix guest CTA card spacing, surface docs on desktop, add placeholder CA pill
73 | 2026-06-24 15:17 | ruby-trivia | fix: don't blank the app when /api/games returns a non-array
74 | 2026-06-24 16:43 | ruby-trivia | docs: add Roadmap page + purge bushleague from user-facing copy
75 | 2026-06-24 16:57 | ruby-trivia | chore: purge bushleague from everything in code (relic — it's only a host name)
76 | 2026-06-24 17:02 | ruby-trivia | chore: set official token contract address (CA pill)
77 | 2026-06-24 17:16 | ruby-trivia | docs: reconcile chain references to Solana (token moved from BSC)
78 | 2026-06-24 17:56 | ruby-trivia | docs: full Roadmap (vision, Now / 30-day / 60-day / Beyond)
79 | 2026-06-24 19:04 | ruby-trivia | fix: trivia sounds = beeps/boops only + tighten quiz spacing
80 | 2026-06-24 19:41 | ruby-trivia | feat(web3): Solana holder-perks layer (web3.ruby-trivia.com)
81 | 2026-06-24 19:49 | ruby-trivia | docs: prod backend handoff — master<->MariaDB divergence (for Odi)
82 | 2026-06-24 20:59 | ruby-trivia | feat(web3 UI): wallet connect in bottom nav + polish (for Odi to integrate)
83 | 2026-06-24 22:50 | ruby-trivia | fix(web3 demo): branding purge, guest mobile nav, emoji PFP, daily-reward + desktop wallet
84 | 2026-06-24 23:17 | ruby-trivia | fix(web3): show wallet Connect in guest mode (sidebar + bottom nav)
85 | 2026-06-24 23:24 | ruby-trivia | fix(nav): guest desktop sidebar 1:1 with mobile bottom nav
86 | 2026-06-24 23:26 | ruby-trivia | fix(i18n): add missing quiz.todaysQuiz key (was rendering raw "quiz.todaysQuiz")
87 | 2026-06-24 23:32 | ruby-trivia | i18n(web3): translate wallet-modal strings into all locales
88 | 2026-06-24 23:40 | ruby-trivia | fix(i18n): translate practice-topic category labels
89 | 2026-06-24 23:48 | ruby-trivia | fix(guest): restore Sign in / Create account CTA on guest profile (mobile login)
90 | 2026-06-25 00:08 | ruby-trivia | fix(deploy): kill labs subdomain — labs.ruby-trivia.com → www.ruby-trivia.com
91 | 2026-06-25 00:28 | ruby-trivia | fix(deploy): actually build + ship the web3 bundle to web3.ruby-trivia.com
92 | 2026-06-25 01:10 | ruby-trivia | fix(web3): error-boundary the wallet nav button so it can't take down the nav
93 | 2026-06-25 02:21 | ruby-trivia | docs: fix stale BNB Smart Chain refs (token is live on Solana)
94 | 2026-06-25 02:26 | ruby-trivia | docs: token ticker is $TRIVIA, not RUBY (Ruby Trivia is the game)
95 | 2026-06-25 04:50 | ruby-trivia | feat(splash): show token CA pill on the welcome/language screen
96 | 2026-06-25 13:26 | ruby-trivia | fix(db): translate SQLite ON CONFLICT upsert to MariaDB ON DUPLICATE KEY
97 | 2026-06-25 13:26 | ruby-trivia | fix(db): translate SQLite ON CONFLICT upsert to MariaDB ON DUPLICATE KEY
98 | 2026-06-25 15:49 | ruby-trivia | fix(web2): hide token CA pill in web2/store builds
99 | 2026-06-25 15:53 | ruby-trivia | fix(web2): hide tokenomics docs article in web2/store builds
100 | 2026-06-25 16:39 | ruby-trivia | feat(store): ship native app as free v1 (no subscribe stub)
101 | 2026-06-25 16:47 | ruby-trivia | feat(live): resilient WS reconnect — backoff, auto-rejoin, graceful fail
102 | 2026-06-25 17:44 | ruby-trivia | docs: app-store distribution plan + session handoff
103 | 2026-06-25 18:12 | ruby-trivia | feat(live): broadcast stage view of live trivia rounds (P0)
104 | 2026-06-25 18:22 | ruby-marketing | Add X Space outline (2026-06-25) + repo README8f80a5bf9ca556506fb5b84005a0be9dcbd610a5 2026-06-26T13:45:01-04:00 ruby-trivia-handbook Handbook: add public titles (Dutch = lead dev, Odi = lead marketing); both doing both
105 | 2026-06-26 09:37 | ruby-marketing | Add manager planning set: state-of-project, idea bank, roadmap, 1/3/7/14/30-day deliverables, team instructions, risks/ops
106 | 2026-06-26 10:00 | ruby-marketing | Sensitivity pass: soften ownership language, ease comp/financials, pull Chess in, detail Day 3
107 | 2026-06-26 10:13 | ruby-marketing | Correct for Magic's departure + add weekend primer
108 | 2026-06-26 10:24 | ruby-marketing | Weekend primer: Lotus/itachi = consultants, Odi runs X, + Saturday Space, challenge-to-play, example posts
109 | 2026-06-26 10:35 | ruby-marketing | Scrub all 'bundle' mentions; reframe Bao/nerd + Lotus/itachi as outside (not team)
110 | 2026-06-26 10:47 | ruby-marketing | Add X Space talking-points cheat sheet (Sat) — beats, soundbites, hard-Q answers, guardrails
111 | 2026-06-26 10:51 | ruby-trivia-handbook | Public handbook: how we work + this weekend (community-facing)2bf7eff9e5d10e38f6bf157372e19db43bc75fda 2026-06-26T15:58:55-04:00 ruby-trivia docs(web3): independent legal/regulatory research report
112 | 2026-06-26 10:59 | ruby-trivia-handbook | Strip theme banner; landing page = just the team + weekend links (nothing above)
113 | 2026-06-26 11:04 | ruby-trivia-handbook | Weekend page: put the actionable plan back (X post examples, thread, challenge copy, Space) — minus internal-only bits
114 | 2026-06-26 11:09 | ruby-trivia-handbook | Add public FAQ (hard questions, cleaned) + link from landing
115 | 2026-06-26 11:16 | ruby-trivia-handbook | Team: Dutch + Odi are the two-person core, tied across everything (not split by frontend/backend)
116 | 2026-06-26 11:23 | ruby-trivia-handbook | Clarify: posts are examples to work from (not post-as-is); designate X = Odi; community = TG (Destiny), not X
117 | 2026-06-26 11:39 | ruby-marketing | Sync private docs to handbook: Dutch+Odi tied across everything; toolkit = examples to work from (not canned posts)
118 | 2026-06-26 12:51 | ruby-trivia | feat(bot): /stats — lifetime avg points per question & per round
119 | 2026-06-26 13:44 | ruby-marketing | Titles + decision structure + capacity/slow-roll across planning set
120 | 2026-06-26 13:45 | ruby-trivia | feat(stats): efficiency averages across all telegram modes + web profile
121 | 2026-06-26 15:53 | ruby-trivia | docs(web3): branch for tokenomics/NFT work + compliance guardrails
122 | 2026-06-29 19:04 | ruby-marketing | Add 06: business-structure & governance scaffold (Delaware umbrella, parallel web2/web3, risk-parity control)
123 | 2026-06-29 19:10 | ruby-marketing | Add 07: tax & legal/regulatory research (cited) for the governance structure
124 | 2026-06-29 19:17 | ruby-marketing | Add 08: latest 2025-26 statutes + how-others-do-it playbooks + right-sized recommended path
125 | 2026-06-29 20:05 | ruby-marketing | Add browsable docs hub (README front page) + S-corp analysis across 06/07/08
126 | 2026-06-29 20:22 | ruby-marketing | Add founder/operator compensation working proposal (24h counter window) to 06; thread through 07/08/README
127 | 2026-06-29 20:50 | ruby-marketing | Comp: operator draw is CAPPED at a fair daily wage (excess stays in treasury)

## Methodology
Methodology & caveats
• HOURS are estimates from commit timestamps. FLOOR = git-hours method (>2h gap = new session, +2h ramp). REALISTIC = active-day method weighted by commit intensity (crunch days like the 6/24 launch ≈16h; normal active days ≈8h).
• Per Dutch's direction, ALL commits under his identity across ALL Ruby repos are counted as his hours (ruby-trivia, dutchiono/ruby-trivia, ruby-labs, ruby-trivia-classroom, ruby-marketing, ruby-trivia-handbook).
• These hours are still a FLOOR for total effort — commits capture only days code was saved; they exclude design, planning, testing, live launch ops, production firefighting, comms, and pre-first-commit work.
• Identity matched: 'dutch <dutchiono@gmail.com>' + GitHub 'dutchiono'. Other contributors' and automated commits excluded.
• RATES: $10/hr is illustrative (to show pennies-on-the-hour). $50/hr is the stated agreed post-launch rate. Market ~$130/hr and the Industry Bid use US senior full-stack/web3 norms.
• 'Already received' is a placeholder ($0) — fill in to finalize the effective rate + the ask.